## UTB
S/N | CHANGE REQUESTS | PRIORITY | START DATE | % COMPLETED | USG COMMENT | TESTED - UTB (Y/N) | IMPLEMENTED (Y/N) | TARGET DATE | COMPLETION DATE | UTB COMMENT | STATUS | File changed
1 | Notch on employees module should be linked to Salaries | M | 2020-11-04 | 100% |  | Y | Y |  | 2020-11-06 |  | Completed
2 | Field for employment type should be displayed on salaries grid | M | 2020-11-04 | 100% | No more relevant | Y | Y |  | 2020-11-06 |  | Completed
3 | Recruitment date should not be same as date of birth | M | 2020-11-10 | 100% |  | Y | Y |  | 2020-11-18 |  | Completed
4 | Data on Salaries Entries Grid should have – Filter by: Department/Branch | M | 2020-11-10 | 100% | No more relevant | Y | Y |  | 2020-11-10 |  | Completed
5 | NASSIT reports should be directly updated | M | 2020-11-05 | 100% | Can be extracted by user | Y | Y |  | 2020-11-10 |  | Completed
6 | Leave approval levels should take generic format: Supervisor => Indirect Supervisor => HR | M | 2020-11-11 | 100% | Allows for users choice of approvers and the order it should go | Y | Y |  | 2020-11-10 |  | Completed
7 | System errors should be specific and understandable | M | 2020-11-14 | 100% |  | Y | Y |  |  |  | Completed
8 | Downloading bio-data from core banking for HR application upload | M | 2020-11-17 | 100% | Not coding problem. Bio-data can be uploaded when needed | Y | Y |  |  |  | Completed
9 | Branch setup should not take duplicates | M | 2020-11-02 | 100% |  | Y | Y |  | 2020-11-02 |  | Completed
10 | “Manage Metadata” should be changed to manage parameters | M | 2020-11-02 | 100% |  | Y | Y |  | 2020-11-02 |  | Completed
11 | “No. of worked days” on salaries entries screen should be replace with “No. of Working Days” | M | 2020-11-02 | 100% |  | Y | Y |  | 2020-11-02 |  | Completed
12 | Name of Bank on staff setup should be removed | M | 2020-11-02 | 100% |  | Y | Y |  | 2020-11-02 |  | Completed
13 | Add filter to payroll reports grid to filter by pay period | M | 2020-11-11 | 100% | A search field has been added to allow users to search for pay period. Users can also filter by Department/Branch | Y | Y |  | 2020-11-11 |  | Completed
14 | Make provision for contract staff salary component entry | H | 2020-11-23 | 100% |  | Y | Y |  |  |  | Completed
15 | Number of working days should be based on employee start date | M | 2020-12-16 | 100% | To avoid limiting the user, a more flexible field has been created to handle working days | Y | Y |  | 2020-12-17 |  | Completed
16 | Parameter for additional allowances should be available | M | 2020-11-23 | 100% |  | Y | Y |  |  |  | Completed
17 | Salary components should auto-allocate to all staff | M | 2020-11-23 | 100% |  | Y | Y |  |  |  | Completed
18 | Stop refreshing notch after updates on salaries | H | 2020-11-23 | 100% |  | Y | Y |  |  |  | Completed
19 | Search Field should be made more visible | M | 2021-01-26 | 100% |  | Y | Y |  | 2021-02-01 |  | Completed
20 | Notch should be added to employee basic information | H | 2021-01-26 | 100% |  | Y | Y |  | 29/02/2021 |  | Completed
21 | Make number of working days "22" for all staff | M | 2021-01-26 | 100% |  | Y | Y |  | 29/02/2021 |  | Completed
22 | Remove pay period for payroll reports filter | L | 2021-01-26 | 100% |  | Y | Y |  | 29/02/2021 |  | Completed
23 | Provide a database backup procedure | H | 2021-01-26 | 100% |  | Y | Y |  | 2021-02-15 |  | Completed
24 | Activate "Search" field on all pages | M | 2021-01-26 | 100% |  | N | N | 2021-06-30 |  |  | In Progress | admin/payrol.js, admin/expense.js, payrol/index.php, expense/index.php
25 | Apply calculation columns to notches | H | 2021-04-01 | 30% |  | N | N | 2021-07-30 |  |  | In Progress
26 | Components like medical excess and Union Dues should be able to spread over a number of months to be paid in installments | M | NOT STARTED | 0% |  | N | N | 2021-06-30 |  |  | NOT STARTED
27 | Display payslip report details per staff on screen | M | 2021-03-01 | 10% | Filter Function allows user to select only one employee to view his/her payslip details | N | N | 2021-07-30 |  |  | NOT STARTED
28 | Do not switch before viewing and downloading payslip of staff | M | NOT STARTED | 0% |  | N | N | 2021-08-30 |  |  | NOT STARTED
29 | Fields taking amount should take commas | M | 2021-03-01 | 100% |  | N | N | 2021-06-30 |  |  | In Progress | src/admin/adminpayrolmanager.php
30 | Navigations should support movement to first page and last page | M | NOT STARTED | 100% |  | N | N | 2021-07-30 |  |  | NOT STARTED | bootstrap-datatable.js
31 | When management level is selected, corresponding job title LOV should filter accordingly. | M | NOT STARTED | 100% |  | N | N | 2021-06-30 |  |  | NOT STARTED | employees.js,get_jobtitles.php,jobs.js
32 | Notch and Paygrade LOVs should depend on Job title | M | NOT STARTED | 100% |  | N | N | 2021-06-30 |  |  | NOT STARTED | employees.js, get_notches.php
33 | LOV for employment type should be added to salaries screen to enable/disable fields based on the employment type selected | M | 2021-10-06 | 100% |  | N | N | 2021-06-30 |  |  | NOT STARTED
34 | Filtered staff on salaries screen should contain totals for all components and total count of all data filtered. | M | NOT STARTED | 100% | Salaries Screen has been removed | N | N | 2021-08-30 |  |  | NOT STARTED
35 | Payroll Report should also have component totals | M | 2021-08-01 | 100% |  | N | N | 2021-08-30 |  |  | NOT STARTED
36 | On salaries grid (or on all other grids), you should be able to export data directly to excel/pdf | M | NOT STARTED | 100% |  | N | N | 2021-07-30 |  |  | NOT STARTED | employees.js employee-index.php, salary.js core/header.php (files where added to the appdownloads folder
37 | Recruitment module should directly link to employee module | M | 2021-04-01 | 100% | Successfully completed | N | N |  | 2021-04-23 |  | Completed
38 | Syncing Bio-data between core-banking and HR application | H | 2021-02-01 | 100% | Successfully completed | N | N |  | 2021-04-16 |  | Completed
39 | Single entry for salary increment for all staff | M | 2021-05-01 | 100% | Successfully completed | N | N |  |  |  | NOT STARTED
40 | Previous and Next buttons not working in all modules | M | 2022-10-02 | 100% | Successfully completed | [6 empty] | js/select2/bootstrap-datatable.js

## USG
S/N | CHANGE REQUESTS | PRIORITY | START DATE | % COMPLETED | USG COMMENT | TARGET DATE | TESTED - ROKEL (Y/N) | IMPLEMENTED (Y/N) | COMPLETION DATE | ROKEL COMMENT | STATUS
1 | Date formats should conform with core-banking date format |  | 2021-05-18 | 20%
2 | Change NIC to NIN in employee bio-data |  | 2021-05-18 | 100% | [6 empty] | Completed
3 | Capture entrance exams for new recruits |  | NOT STARTED | ON HOLD
4 | Capture labour card number for recruits and employee |  | 2021-05-18 | 100% | [6 empty] | Completed
5 | Capture fit and proper with document attachment |  | 2021-05-18 | 100% | [6 empty] | Completed
6 | Staff number should be changed after being re-employed or restored |  | 2021-05-19 | 100% | Restore feature has been deactivated, making it easy to generate new employee id | [5 empty] | Completed
7 | You should not be able to reactivate terminatd employees |  | 2021-05-19 | 100% | [6 empty] | Completed
8 | Overtime capturing and calculation |  | 2021-05-19 | 100% | Overtime Request Available in the system | [5 empty] | Completed
9 | Within working hours, breaks like lunch, out of office activities etc should be captured |  | 2021-05-19 | 100% | [6 empty] | Completed
10 | Clocking at different branches apart from original branch of staff should be enabled but catpure the location |  | 2021-05-19 | 100% | Can be configured on the application | [5 empty] | Completed
11 | Leave allowance indicator to show if you have been paid |  | 2021-05-19 | 20% | [6 empty] | In Progress
12 | Staff on leave filtering (by position, by department etc) |  | 2021-05-19 | 100% | [6 empty] | Completed
13 | Suspension and salary management |  | NOT STARTED | NOT STARTED
14 | Flat rate of salary increase should be possible |  | 2021-06-01 | 100% | [6 empty] | Completed
15 | There should be approval hierarchy for payroll |  | NOT STARTED | NOT STARTED
16 | There should be summary totals for each salary component |  | NOT STARTED | NOT STARTED
17 | Allow for imprest without receipt as a comment field |  | 2021-05-19 | 100% | [6 empty] | Completed
18 | Capture total cost of training |  | 2021-05-19 | 100% | [6 empty] | Completed
19 | Training mudule should be assigned to training managers |  | 2021-05-19 | 100% | Can be configured on the application | [5 empty] | Completed
20 | Asset module may not be needed because of the asset module in core banking |  | 2021-05-19 | 100% | Can be configured on the application | [5 empty] | Completed
21 | Staff loans should be completed |  | NOT STARTED | NOT STARTED
22 | Medical module to handle medical excesses |  | NOT STARTED | 10%
23 | Enable salary reversal on the HR app |  | NOT STARTED | NOT STARTED
24 | NASSIT and PAYE reports (Excel & PDF) |  | NOT STARTED | NOT STARTED
25 | Automate notification for dependents whose ages get to 18 |  | NOT STARTED | NOT STARTED
26 | Staff account opening should be initiated from HR |  | 2021-06-01 | 90%
27 | Announcements should also be sent via email or SMS |  | NOT STARTED | NOT STARTED
28 | Prizes after appraisal |  | NOT STARTED | NOT STARTED
29 | Customer account creation on new employee setup |  | NOT STARTED | 100%
30 | Create modal to add reason for terminating staff |  | NOT STARTED | 100%
31 | Add approval to employee creation |  | NOT STARTED | 100%
|  |  | 2021-06-09 | 100%

## ROKEL
S/No | Issue/Description | Details | % COMPLETED | Resource | Priority | Start Date | In Charge | Target Date | End Date | Comment
1 | HUMAN RESOURCES - STAFF RECRUITMENT | It was agreed that the date format on the HR API must be synchronized to match that in the Core Banking application. | 20% | HR |  | 2021-05-19 | Paul | 2021-06-30 | 2021-05-19 | This is currently not supported
2 | HUMAN RESOURCES - STAFF RECRUITMENT | It was noted that IT would create their feed from the HR application to the Core Banking application. | 100% | HR |  | 2021-05-19 | Paul |  | 2021-05-19 | Working
3 | HUMAN RESOURCES - EMPLOYEE SET-UP | It was noted that the entrance examination is a requirement in the recruitment process. It was agreed that process be filtered into the HR API so that the exams are held online and in real-time. | ON HOLD | HR
4 | HUMAN RESOURCES - EMPLOYEE SET-UP | It was agreed that under the employee set up screen, USG should add the following fields for the employee details- | 100% | HR
5 | HUMAN RESOURCES - EMPLOYEE SET-UP | The Field for Labour Card number to be optional | 100% | HR
6 | HUMAN RESOURCES - EMPLOYEE SET-UP | The Field for National Identification Number (NIN), to be made mandatory. | 100% | HR
7 | HUMAN RESOURCES - EMPLOYEE SET-UP | An optional field to be included for fit and proper test for senior Management staff recruitment | 100% | HR
8 | HUMAN RESOURCES - STAFF TERMINATION IN THE SYSTEM | It was agreed that the Field to reactivate a staff is disabled so that a new staff ID will be generated by the system upon re-installment of a previously terminated staff. | 100% | HR
9 | HUMAN RESOURCES - STAFF TERMINATION IN THE SYSTEM | It was also noted that this module could be used to set staff on suspension and to define whether they are to be on half-pay, full-pay, or whatever. | 100% | HR |  |  |  | 2021-06-30
10 | HUMAN RESOURCES - EMPLOYEES ATTENDANCE MONITOR | It was noted that two devices would be required at any location, one for clock-in and another for clock-out. | 100% | HR |  | 2021-05-19 | Paul | 2021-05-19 | 2021-05-19 | Applicable
11 | HUMAN RESOURCES - EMPLOYEES ATTENDANCE MONITOR | It was also noted that clock-in and clock-out could be done multiple times in a day, depending on your function. Where there is a breakdown in the device, clock-in and clock-out will be done manually until the device is reinstated. After that, the records will be updated in the system by HR. | 100% | HR |  | 2021-05-19 | Paul | 2021-05-19 | 2021-05-19 | Applicable
12 | HUMAN RESOURCES - STAFF LEAVE MANAGEMENT – | Here a staff's leave is set up. After some demo, HR should provide the number of leave days for various categories of employees for USG to capture into the system. It was requested that the system provide all staff on leave at any point in time in graphical order. It was agreed that the graphs be color quoted for different types of leave for easy identification. | 100% | HR |  | 2021-05-19 | Paul | 2021-05-19 | 2021-05-19 | Applicable
13 | HUMAN RESOURCES - STAFF LEAVE MANAGEMENT – | It was agreed that an optional field is included in the Leave application portal for confirmation for Leave allowance to be paid. | 100% | HR |  | 2021-06-14 | Paul | 2021-06-15 |  | Completed
14 | HUMAN RESOURCES - STAFF LEAVE MANAGEMENT – | It was also agreed that a portal is created where a particular category of staff can be captured and differentiated into those currently on leave and those at work. | 100% | HR |  |  | Paul
15 | PAYROLL SET-UP | It was noted that where there is a percentage increase in salary or allowances across the board, the system should be able to apply the same. | 100% | HR |  |  | Paul
16 | PAYROLL REPORT | It was agreed that there should be an additional Field for a verifier before final approval by HR. It was noted that HR is to provide a chain of approval so that USG can incorporate it into the system. | 100% | HR |  |  | Paul | 2021-06-30
17 | PAYROLL REPORT | There should be a summary of the payroll report so that an approver may not need to see the entire documents. | 100% | HR |  |  | Paul | 2021-06-30
18 | EXPENSE SET-UP | It was agreed that there should be a field for Limit set-up under this screen. | 100% | HR |  |  | Paul | 2021-06-30
19 | EXPENSE SET-UP | There should be an optional field for expenses without receipt at the set-up. | 100% | HR |  | 2021-05-19 | Paul | 2021-05-19 | 2021-05-19
20 | TRAINING MODULES | It was agreed that a template for a certificate of Award could be designed by the system. | 100% | HR |  |  | Paul | 2021-07-30
21 | TRAINING MODULES | It was agreed that the system should be able to apportion costs of staff sent for training from each department or unit, so that the cost goes to the respective staff's unit or department or branch. | 100% | HR |  | 2021-05-19 | Paul | 2021-05-19 | 2021-05-19
22 | DOCUMENT MANAGEMENT MODULE | Under Documents type, there should be add-ons on the option in the system. | 100% | HR |  | 2021-05-19 | Paul | 2021-05-19 | 2021-05-19
23 | COMPANY ASSETS (ADMIN) | This helps HR identify certain assets in their own department that match company assets to staff. It is noted that HR does not need this module and that it should be transferred to Admin. | 100% | HR |  | 2021-05-19 | Paul | 2021-05-19 | 2021-05-19 | Applicable
24 | STAFF MEDICAL LIMIT - | Here, it was agreed that a separate module is set up to monitor the usage of staff medical limits. | 100% | HR |  |  | Paul | 2021-06-30
25 | l | It was agreed that in the HR module, all categories of staff medical limit to be provided by HR for USG to input into the system to be able to monitor limit overuse. Also, dependants are to be part of the medical allowance of the employee. | 100% | HR |  | 2021-05-18 | Paul
26 | STAFF MEDICAL LIMIT - | NASSIT contribution to be set up into the system and a report can be generated indicating the employee's contribution and employer's contribution. So that an employee can be able to monitor and reconcile his/her USG NASSIT statement and the actual statement received from NASSIT. | 100% | HR |  | 2021-05-18 | Paul
27 | STAFF MEDICAL LIMIT - | It was agreed that USG design reports for PAYE, NASSIT, NRA, etc., to be added to the list of reports in the system. | 100% | HR |  |  |  | 2021-06-30
28 | STAFF MEDICAL LIMIT - | It was agreed that for reports design, the departments or units should provide their template to USG for input, and it was also noted that the information we capture at the set-up stage would help us design our reports. | 100% | HR |  | 2021-05-18 | Paul
29 | STAFF DIRECTORY – This is where staff personal details are captured | It was noted that the information on the Core Banking application would not filter down into the HR module details on staff because they are two different platforms. However, after lengthy deliberations, it was agreed that the Core Banking Application could be synchronized with the HR API to share staff information. | 100% | HR |  | 2021-05-18 | Paul | 2021-05-31 |  | Finishing Touches
30 | END OF SERVICE BENEFITS – | It was noted that this is a static data amendment issue set up in the system. | 100% | HR |  |  | Paul | 2021-06-30
31 | PERFORMANCE MODULE – | It was noted that this is still a ‘work in progress’. | 100% | HR |  | 2021-05-19 | Paul | 2021-05-31 | 2021-05-19
32 | Relieve Duties | Module for relieving staff duties
33 | Out-station Allowance
34 | Relocation Allowance | Allowance for relocated staff

## SLCB
S/No | Issue/Description | % COMPLETED | Resource | Priority | Start Date | In Charge | Target Date | End Date | Comment
COMPLETE HR MANAGEMENT APP
1 | Ability to create departments and sub departments with unit heads and subunit heads up to 6 levels | 100% | HR |  |  | Paul
2 | Document Management capability scanners for HR - document scanning appended to transactions | 100% | HR |  |  | Paul
3 | data capture staff country of residence and country of origin (nationality) | 100% | HR |  |  | Paul
4 | Date of recruitment. Add start date so probation period can be calculated, the confirmation date computed. 30 days advance notice to confirmation | 70% | HR |  | 2021-08-30 | Paul
5 | Ability to load as many qualifications linked to staff | 100% | HR |  |  | Paul
6 | Ability to load specific job profiles and link to staff | 100% | HR |  |  | Paul
7 | Ability to report on individual staff qualification gaps (Difference between own qualification and job profile requirement) | 80% | HR |  | 2021-08-30 | Paul
8 | Specific Job profiles should fall into categories (General, Core and Technical + if any) | 100% | HR |  |  | Paul
9 | Staff ability to log-in to personal page with a dashboard of competence gaps, eLearning, Gaps, Leaves overdue, any other non-conormities | 100% | HR |  |  | Paul
10 | Abiliity of SLCB to place General notice on individual log-in pages | 100% | HR |  |  | Paul
11 | Ability to allow each staff and manager to establish training needs of individuals tied to roles | 100% | HR |  |  | Paul
12 | Ability to define each staff career and succession plans. Amend and Delete | 100% | HR |  |  | Paul
13 | Course Profiles Pre-loaded into system | 100% | HR |  |  | Paul
14 | Online courses must be interfaced to HRM | 100% | HR |  |  | Paul
15 | Course Category - In-house, In-country, external training, external attachment | 100% | HR |  |  | Paul
16 | Module to load individual performance objectives | 100% | HR |  |  | Paul
17 | NB: Objectives will be loaded by staff, approved by LM and finally accepted by HR. Another Leg, High level objectives loaded and these cascaded down the hierarchy | 80% | HR |  | 2021-08-30 | Paul
18 | By annual (6monthly) appraisal - INTERIM $ FINAL (Interim by June; Final by December) | 100% | HR |  |  | Paul
19 | General Comments for staff; and general comments for manager; training needs for staff; trainig needs recommended by manager. Staff must finally accept or reject Manager appraisal before it goes to HR for rationalization | 100% | HR |  |  | Paul
20 | HR to provide Appraisal & Objective format for configuration into the system | 100% | HR |  |  | Paul |  |  | System is ready for configuration
21 | Ability to handle INFRACTION (PENALTIES) management | 100% | HR |  |  | Paul
22 | Ability to maintain Salary Scales and linked to individuals | 100% | HR |  |  | Paul
23 | Scales must be subdivided into notches | 100% | HR |  |  | Paul
24 | It should be possible to do mass movement of every staff by say 2 notches (in which case if a range is full, move to the next range) | 20% | HR |  | 2021-08-30 | Paul
25 | Ability to load annual leave - Leave plan per staff to be loaded | 100% | HR |  |  | Paul
26 | Ability to take leave in portions, however, block leave must be first | 100% | HR |  |  | Paul
27 | Leave Types | 100% | HR |  |  | Paul
28 | Once HR approves a voucher is generated auto to finance for two (2) stage approval. Account credited automatically; email sent to manager and staff | 65% | HR |  | 2021-08-30 | Paul
29 | Payment is for only block leaves | 20% | HR |  | 2021-06-30 | Paul
30 | Leave Allowance is fixed per category | 10% | HR |  | 2021-06-30 | Paul
31 | Staff leave request - Add comments for line manager approver | 100% | HR |  |  | Paul
32 | Ability to Recall Staff from leave | 100% | HR |  |  | Paul
33 | INFRACTION - Ability to attach any number of supporting documents | NOT STARTED | HR |  | 2021-08-30 | Paul
34 | SEVERANCE Transaction - to take care of REGISTRATION, TERMINATION, SEVERANCE DUE TO RESTRUCTURING | 100% | HR |  |  | Paul
35 | MEDICAL ATTENDANCE - Ability to keep track of Medical attendance/records. Access restricted to only authorized persons. | 60% | HR |  | 2021-07-30 | Paul
| STAFF TRANSFER |  | HR |  |  | Paul
37 | Ability to transfer staff | 100% | HR |  |  | Paul
38 | Transfer is either by HR or staff line manager (or initiated by line manager and approved by HR or Manager of line-manager) | 60% | HR |  | 2021-08-30 | Paul
39 | Transfer must be acknowledged by new manager before becoming effective | 60% | HR |  | 2021-08-30 | Paul
40 | Transfer History must be maintained in the system for the work life of the staff and also archived for the retention period | 100% | HR |  |  | Paul
41 | Ability to maintain a history of all activities on staff data for as long as staff is in employment | 100% | HR |  |  | Paul
42 | Ability to Archive staff data when staff leaves service for as long as national data retention period | 100% | HR |  |  | Paul
43 | Managing employee and user creation (Employee Levels) | 100% | HR |  |  | Paul
44 | Create leave and appraisal on behalf of non-users (Contract Staffs) | 100% | HR |  |  | Paul
45 | Ability to calculate wage per day | 100% | HR |  |  | Paul
46 | System should be able to create Management, Non-Management and Senior Management staff. | 100% | HR |  |  | Paul
47 | Retirement notification six month ahead | 60% | HR |  | 2021-07-30 | Paul
48 | Leave notification two months ahead | 60% | HR |  | 2021-07-30 | Paul
49 | New Tab for Employee Work Experience | 70% | HR |  | 2021-07-30 | Paul
50 | Biometric Attendance System Integration | 100% | HR |  |  | Paul
51 | Ability to process staff monthly payroll and link to monthly/annual budget performance | 100% | HR |  |  | Paul
52 | CBA - access to core banking and revocation when staff is transferred or exits | 100% | HR |  |  | Paul
| GENERAL LEDGER |  |  |  |  | Paul
54 | expense management | 100% | HR |  |  | Paul
55 | Salary Uploads to CBA | 100% | HR |  |  | Paul
56 | Finance Expense integration with Payroll system | 100% | HR |  |  | Paul
57 | Finance Expense integration with HR system | 100% | HR |  |  | Paul
58 | Complete Payroll processing | 100% | HR |  |  | Paul